Statement of Work

For

Total Service Solutions (TSS)

Arlington Academy of Hope (AAH) Technology Assessment

July 14, 2010

### Background

Arlington Academy of Hope is a model community school with a primary purpose to provide quality education and basic healthcare to children in rural Uganda.  AAH operates a model primary school in the Bududa District of eastern Uganda and works closely with local education officials and school administrators in ten local village schools to address the basic learning needs of primary and secondary school students.   AAH trains teachers, provides scholarships, learning materials, uniforms and meals to students and has begun to focus on the unique challenges girls face through mentoring activities.

With an estimated 54,000 school age children in Bududa, it is predicted that only one in ten will attend, complete primary school, and continue on to secondary school.  Therefore, in addition to continuing its scholarship program, AAH through its Outreach Program seeks to improve the quality of learning through teacher training and mentoring for ultimately ten thousand school age children at ten village schools in Bududa and neighboring Manafwa Districts.  The program currently provides school supplies, books, soccer balls and uniforms, scholarships to select top performing students, and incentives to teachers demonstrating exceptional commitment and performance.

The AAH Outreach network consists of 18 schools in the four districts of Bududa, Manafwa, Mbale and Sironko, an orphanage and vocational center in Bududa, and a school for disabled children in Kampala.

Some of AAH’s outreach program activities have provided:

- School supplies, including pens, pencils, books, crayons, erasers, etc.

- Teacher training for teachers in these partner schools

- Field trips for schools participating in the outreach program

- Providing soccer balls and other play equipment

- Organized joint music and drama programs with other schools

- Provided nutritional meals to students at outreach schools

- Entertainment including movies to outreach schools

- Support to local communities including churches in support of initiatives

The 18 Outreach schools require better coordination.  Due to high costs of transportation, outreach school students and teachers are unable to travel to AAH regularly. While AAH has an advanced academic program, it is difficult to deliver these quality programs to the schools in their network.  One solution is to take advantage of technological advances to deliver learning to these schools through a shared network since the total school network area is within a 20 mile radius.  AAH currently employs computer literate staff capable of managing an information and communication technology (ICT) network that would meet the needs of AAH’s outreach program.

AAH’s goal will be to utilize ICT to deliver effective learning not just at AAH, but to the entire AAH outreach network.  Computers will enhance learning at the school through the use of educational CDs, printing, overhead projection, and sound.  Any ICT services would also provide internet connection, either through satellite connection, or mobile phone link up and a local or wireless network that can connect the schools to each other.  AAH has been pursuing opportunities for satellite link up with schools in the U.S.A. and other organizations.

AAH outreach schools

| School | Sub-county | District |
| --- | --- | --- |
| Bumwalukani Primary School | Bulucheke | Bududa |
| Bulobi Primary School | Bukigai | Bududa |
| Bumwalye Primary School | Bulucheke | Bududa |
| Bushika Primary School | Bushika | Bududa |
| Bukigai Primary | Bukigai | Bududa |
| Bunandutu Primary School | Bumayoka | Bududa |
| Bududa Primary School | Bududa | Bududa |
| Bubita Primary School | Bubita | Bududa |
| Manjiya Primary School | Bududa Town Council | Bududa |
| Bukhaukha primary School | Bushika | Bududa |
| Bududa Vocational Center | Bududa | Bududa |
| Matuwa Primary School | Bupoto | Manafwa |
| Bupoto Primary School | Bupoto | Manafwa |
| Toma Buta Primary School | Bugobero | Manafwa |
| Lwandubi Primary School | Buwabwala | Manafwa |
| Tubei Primary School | Bukiende | Mbale |
| Buyobo Primary School | Buyobo | Sironko |
| Bukambule Primary School | Budadiri | Sironko |
| Canaan School for Disabled | Kampala | Kampala |
| US Sister Schools |  |  |
| Arlington Traditional School | Arlington | VA |
| Children’s International School | Arlington | VA |
| Gunston Middle School | Arlington | VA |
| Lakeside School (developing relationship) | Seattle | WA |
| American University | Washington | DC |

### Scope

Under this scope of work, a team from Total Service Solutions (TSS) will travel to Uganda to conduct a technical study and determine the feasibility and sustainability of possible ICT solutions for AAH.  The TSS team will meet with appropriate schools, businesses, academic, and possible government officials and solicit their advice and guidance which will help define key elements for achieving a successful, and most importantly, financially self-sustaining ICT project. Ugandan Telecommunication Companies (MTN, Mango, Celtel) will also be assessed to determine areas of coverage and potential support for an AAH/ICT project through public and private partnerships.  The use of solar power systems and backup generators will be evaluated.

Statistical data on social sector service plays an important role in developing and implementing appropriate programs to meet the needs of communities.  During the course of this assessment, TSS will also conduct an assessment of AAH’s community-driven data collection methods for social sector services (health & education) to determine how data is collected, who is involved with data collection (how it is coordinated), who are the end users of the data (MoE, communities, etc), and what the collected data is used for.  Based on initial findings, TSS will also explore what data collection means for the community in terms of the relevance of data and how the community is impacted.

The primary purpose of this assessment is to analyze existing technology infrastructure and recommend a plan for instituting an ICT program that will meet AAH’s educational needs.  This scope does not include implementation.    Following the assessment, TSS will recommend a course of action to AAH in a detailed report.  A section of this report will include the findings from the analyses of AAH’s data collection process.

As part of the ICT assessment, TSS will perform of the following tasks:

- Develop and ICT plan that includes hardware and software requirements

- Determine costs and sources of funding

- Outline an implementation plan

- Determine usage and maintenance issues

- Determine long and short term benefits of the ICT plan

The TSS Assessment Team will consist of 3 consultants whose responsibility will include data collection, assessing the ICT infrastructure environments, and evaluating the usability of an existing information enterprise.   The team will report critical findings, and recommend unbiased, viable solutions for AAH.  In addition, TSS will perform general technology data analysis and collection by interviewing the teachers, students, companies providing infrastructure and ICT solutions. The TSS assessment will also meet with the Uganda Ministry of Education (UMOE) to discuss their future goals for the country and review any proposed ICT implementation plans.  The data collected from this assessment may be shared with the UMOE for the purpose of determining how to best provide funding, ICT solutions, outreach, and improve the education system.

In compiling a report, TSS will also focus on data collected by Peace Corps, UMOE and any other relating sources.  TSS will assess this data in relation to the following parameters;

- Student Attendance records

- Teacher attendance records (Uganda has the highest teacher absence rate in the world 29%)

- Student performances (term tests and final exam results will be computerized)

- Stock systems and inventories (textbooks, supplies, etc)

TSS will assess and evaluate how current data is collected and determine if ICT can improve data collection, and overall use of the data.   TSS will review how ICT solutions will manage, track, distribute, and store information pertaining to:

- Shared lesson plans and teacher instructional materials

- Teacher training via video and webcast

- Electronic/digital teaching materials (DVDs, electronic documents)

- Downloadable content from a network/hub

- Internet accessibility

- Share content and materials from UMOE and other related sources.

- Improved communication within the national and external network (e-mails, file transfer, etc)

- Computer literate staff and students

- Commodity prices, market information, weather forecasts, etc

Team Composition

The Team Leader will maintain overall responsibility for the assessment engagements and determine consultant assignments, manage travel logistics, and play an active role interviewing key management personnel to clarify their issues and concerns ensuring ultimate satisfaction with the assessment.

The Information and Communication Technology Specialist is responsible for examining enterprise business functions including any existing software applications, hardware, ISPs, distance learning and all other ICT requirements for project implementation.  The consultant will meet with Ministers and school personnel to identify issues and concerns; he/she will diagram the high-level business process, record pertinent observations, develop a critical issues list, and provide recommendations for the final management report.

The in-country Information Technology Consultant will focus on schools and evaluate electrical constraints and resources, determine cost models, and review overall infrastructure issues that may affect ICT partnership programs.  The consultant will be an expert with program linkages and past experience and in-depth knowledge of national and international programs, he/she will utilize past relationships and contacts to assist in the final analysis of the capability of schools to develop long-term educational partnership with other institutions and programs.  The consultant will record all pertinent observations and match any internal programs with existing international requirements. He/she will develop a critical issues list and provide recommendations for the final report.

Draft Work Plan: Proposed Schedule for the assessment August 8 – 31 2010

| Date | Time | Activity Description |
| --- | --- | --- |
| 8/7 |  | Depart Washington, DC |
| 8/8 |  | Arrive Kampala, Uganda |
|  | 11:00 – 1:00 | Introductory meeting in Kampala – Meet Mr. Masumbu (Presidential Advisor on IT) and Dr. Dan Nkaada, the Commissioner for Primary Education in Ministry of Education |
| 8/9 | 3:00 | Travel to Bududa District |
| 8/10 | 9:00 – 10:00 | Introductory Meeting – District Education Officer, Bududa |
|  | 11:00 – 3:00pm | Meet staff and students at AAH. Visit facilities. Assess state of current IT services |
|  | 4:00 | TSS Meeting to review days activities and plan ahead |
| 8/11 | 9:00 – 11:00 | Travel to Bumwalukani Primary School, Review and Assess |
|  | 12:00 – 2:00 | Travel to Bulobi Primary School, Review and Assess |
|  | 3:00 – 5:00 | Travel to Bumwalye Primary School, Review and Assess |
| 8/12 | 9:00– 11:00 | Travel to Bunandutu Primary School, Review and Assess |
|  | 12:00 – 2:00 | Travel to Bubita Primary School, Review and Assess |
|  | 3:00 – 5pm | Travel to Bukigai Primary School, Review and Assess |
| 8/13 | 9:00 – 11:00 | Travel to Matuwa Primary School, Review and Assess |
|  | 12:00 – 2:00 | Travel to Bupoto Primary School, Review and Assess |
|  | 3:00 – 5:00 | Travel to Lwandubi Primary School, Review and Assess |
| 8/14 | 9:00 – 1:00 | Meet with Staff of AAH to review Week’s meetings |
| 8/16 | 9:00 – 11:00 | Travel to Bushika Primary School, Review and Assess |
|  | 12:00- 2:00 | Travel to Bukhaukha Primary School, Review and Assess |
|  | 3:00 – 5:00 | Travel to Bududa Vocational Center, Review and Asess |
| 8/17 | 9:00 – 11:00 | Travel to Bududa Primary School, Review and Assess |
|  | 12:00 – 2:00 | Travel to Manjiya Primary School, Review and Assess |
|  | 3:00 – 5pm | Meet with the Bududa District Education Officer and District officials |
| 8/18 | 9:00 – 11:00 | Travel to Toma Buta Primary School, Review and Assess |
|  | 12:00 – 4:00 | Meet with Manafwa District Officials |
| 8/19 | 9:00 – 11:00 | Travel to Tubei Primary School, Review and Assess |
|  | 1:00 – 5:00 | Meet with Mbale District Officials. Stay overnight in Mbale |
| 8/20 | 9:00: - 11 | Meet with Buyobo Primary School, Review and Assess |
|  | 12:00 – 2pm | Meet with Bukambule Primary School, review and Assess |
|  | 3:00 – 5pm | Meet with Sironko District Officials. Stay in Sironko |
| 8/21 | 9:00 – 12:00 | Meet Budadiri MP, other government officials |
| 8/23 | 9:00 – 5:00 | Meet at AAH, Review Data Collected, Fill gaps |
| 8/24 | 9:00 – 5:00 | Meet at AAH, Review IT services, Plan |
| 8/25 | 9:00 – 5:00 | Meet at AAH, Interview, Plan |
| 8/26 | 9:00 – 5:00 | Travel to Kampala, Visit Canaan School |
| 8/27 | 9:00 – 1:00 | Meet with Ministry of Education officials |
|  | 2:00 – 5:00 | Visit Uganda International School in Kampala. See Advanced IT facilities |
| 8/28 |  | Kampala – Visit other school facilities, Makerere University |
| 8/30 | TBD | Out Briefing with USAID Mission |
| 8/30 |  | Depart Kampala, Uganda |
| 9/1 |  | Begin preparation for Recommendation Report |
| 9/4 |  | First draft of Recommendation Report and Cost Strategy Report |