## Sheet1
Task | Task Name | Notes | Milestone | Duration | Start Date | Est. Finish Date | Pred | Resource | Status | Completed Date | Resource Adj. | Comments
1 | Kickoff Meeting | Review the project scope, time frame and resource | No | 1 day | 2004-03-30 | 2004-03-30 |  | Team | Completed | 2004-03-30 |  | Identify the responsibility
2 | Project Plan | Layout the project plan detail and Outline | No | 2 days | 2004-04-03 | 2004-04-04 |  | Lisa | Completed | 2004-04-05 |  | Require additional info based on Prof. Burns request
3 | Setup server and database | Request the database to setup for the matrix server | Yes | 7 days | 2004-04-04 | 2004-04-10 |  | Arvinder, Ardian | Completed | 2004-04-08 |  | On Time
4 | ER Diagram | Design the ER-Diagram and tables | No | 6 days | 2004-04-05 | 2004-04-10 | 3 | Arvinder, Ardian | Completed | 2004-04-08 |  | On Time
5 | Interface Screen | Use Front-page to design the HTML screen | No | 3 days | 2004-04-10 | 2004-04-16 | 4 | Andrew, Lisa | Completed | 2004-04-15 | Arvinder, Ardian | Due to the technical skill this responsibility shift to Arvinder and Ardian
7 | Review Meeting | At Pace Cafeteria from 11:00 am - 1:00 pm | No | 1 day | 2004-04-17 | 2004-04-17 |  | Team | Completed | 2004-04-17 |  | Review the project status
6 | Diagrams | Create Work Flow, Data Flow, Use Cases Diagram | No | 4 days | 2004-04-17 | 2004-04-26 | 4 | Andrew, Lisa | Completed | 2004-05-08 |  | Andrew will handle Work Flow and Data Flow Diagram. Lisa will handle Use Cases Diagram. Waiting for Andrew to meet with Prof. Burns to complete the diagram.
8 | Programming | Coding and develop the module | Yes | 7 days | 2004-04-18 | 2004-04-24 | 6 | Arvinder, Ardian | Completed | 2004-04-25
| Code Review Meeting | At Pace | No | 1 day | 2004-04-25 | 2004-04-25 |  | Arvinder, Ardian | Completed | 2004-04-25 |  | Arvinder and Ardian met at Pace to review the code.
9 | QA/Testing | Testing the program | No | 2 days | 2004-04-25 | 2004-04-26 | 10 | Andrew, Lisa | Completed | 2004-04-28 |  | Completed.
10 | Documentation | Prepare Documentation for project and presentation | No | 5 days | 2004-04-27 | 2004-05-01 |  | Andrew, Lisa | Completed | 2004-05-09 |  | Send to all the team members for review.
12 | Instruction and Source Code | Prepare Manual Instruction and provide Source Code | No | 3 days | 2004-05-02 | 2004-05-04 |  | Arvinder, Ardian | Pending |  |  | Ardian will provide the final manual instruction and source code.
13 | Finalize the Documentation | Finalize Documentation | No | 3 days | 2004-05-05 | 2004-05-07 |  | Andrew, Lisa | Completed | 2004-05-10 |  | Completed.
14 | Prepare for the presentation | Paper due and prepare for presentation | No | 3 days | 2004-05-08 | 2004-05-10 |  | Team | Ready | 2004-05-11 |  | Send all the documents to Prof. Burns.