Using Scrum and Agile in the Project

Scrum Implementation

Roles

- Product owner – 1 student

  - Owns the Product Backlog

  - Maintain the Product Backlog

  - Accept or reject the implementation of a user story at the end of the sprint

- Scrum master – 1 student

  - Make sure the team implements Scrums – Role, Ceremonies and Artifacts etc

  - Find solutions to the problems of the team

  - Makes sure everything is updated in Github. If not, follow up with the team to have the artifacts updated

- Developers

  - Communicate

  - Design

  - Code and refactor code

  - Test

  - Maintain code

  - Maintain artifacts

  - Produce demo video

  - Attend the required ceremonies

  - Update the required artifacts

- Process coach – Dr. Scharff

  - Provide weekly guidance to the Scrum team

  - Provide feedback based on the audits

- Testers – Team itself and external testers

  - Submit bug reports

  - Summarize a report on the quality of the developed app

- Content managers – 1 student

  - In charge of gathering the content

  - Content must not be copyrighted or sources have to be checked

- Auditors – External team

  - Audit the process and artifacts produced by the team

Ceremonies

- Do 2 Scrums / week on Monday and Wednesday

- Do the sprint planning in one day at the beginning of a sprint

  - Each tasks is estimated

  - The sprint goal is publicly available

  - The US are decomposed into tasks and assigned to the Scrum team

- Prepare and update the sprint demo & retrospective

Artifacts

- Produce the Sprint Goal at the beginning of a Sprint (1st day of the Sprint), i.e., the stories that will be implemented during the Sprint

- Tasks for the Sprint (1st day of the Sprint), i.e., the decompositions of the stories that will be implemented during the sprint

- Produce and maintain the Product Backlog

  - User stories with number of points (difficulty) and priority

  - New stories may be added to the Product Backlog during the Sprint

- Produce and maintain the Sprint Backlog

  - Tasks with estimations and corrections of the estimations during the project

- Scrum logs are available with the 3 questions

  - What did I accomplish since the last Scrum?

  - What will I do until the next Scrum?

  - What obstacles are impeding my progress?

- Bug reports are available

- Produce a Burndown chart at the end of each sprint

Agile Implementation

- The Product Owner acts like an active customer

- Requirements are written as User Stories that are prioritized

- The evolution of the Product Backlog is tracked

- The project is divided into Sprints

- Team uses pair programming (at least once during one sprint)

- Team uses a coding standard

- Code is regularly refactored

- Team uses a code repository (Github) and git

- Testing is done early and often, and integrated throughout the project lifecycle (by developers and testers)

Additional guidelines for Design

- Produce an overall architecture of the app

- Produce different design options (e.g., UML)

- Use design patterns

- Produce a UI design using Cacoo, Ninjamock, popapp or similar

At the end of each sprint, the team produces a demo and a Sprint retrospective

- Sprint goal

- Number of stories planned versus implemented

- Planned versus actual velocity

- Sprint retrospective written summary

  - What should the team start doing?

  - What should the team stop doing?

  - What should the team continue doing?

  - (in terms of process, communications etc)

- Status of the evolution of the Product Backlog

- Burndown chart for the sprint

- Statistics from GitHub

- Video demo of the application (YouTube link)

- Status of the software to be developed - summary.

- Icon of the app

- 3-5 screenshots

- Apk, link or equivalent

Testers test the app at the end of each Sprint.

- US have acceptance test for each user story

- Testers test at the end of each Sprint by using the documentation and artifacts. They also communicate with the developers.

- Testers test using emulators

- Testers test using phones and tablets

- Testers submits bugs in GitHub

- After testing, testers submit a testing report on their team (using the provided template)

- Testers post their testing report

Auditors edit the process used by the Scrum team

- Auditors use a checklist to audit the process at the end of each Sprint. They use all the artifacts available on the wiki.

- After the audit, auditors submit an audit report on their team (using the provided template)

- Auditors post their testing report

Use of a tool to support the software development process model

- GitHub is used to support Scrum

- Requirements are in an Excel spreadsheet and GitHub (Product Backlog and User Stories)

- For each sprint:

  - Design is made available

  - Sprint Goal is made available

  - Scrums are made available

  - Sprint Retrospective is made available

  - The Code Convention of the team is made available

  - The Process Coach and auditors comments are made available

  - The testing report is made available

  - Bugs are submitted using the bug tracking system

Communications

- Each team uses different communication tools.